## DZ 11
Record of HM
Equipment |  |  | : | Bulldozer
Specification |  |  | : | KOMATSU, D85ESS-2
UA Asset Number |  |  | : | DZ2054
User Number |  |  | : | DZ 11
Attachment Name |  |  | : | BLADE, RIPPER,
User |  |  | : | PT. BUMI SUKSESINDO
Location |  |  | : | BANYUWANGI
Periode |  |  | : | 19 October 2023 s/d 04 February 2024 = 109 Hari
No. | Date | Hours Meter (HM) | [5 empty] | Attachment Name | Remark | Day |  | Night |  | Total HM | Delay | [9 empty] | Total Delay | IDLE |  | Total Idle | BREAKDOWN |  |  |  |  | Total Breakdown | PA(%) | Total All | Check | UA(%) | DEDUCTION | Day Shift |  | Night Shift
|  | Day Start | Day Finish | Total Shift 1 | Night Start | Night Finish | Total Shift 2 |  |  | Operator | Lokasi | Operator | Lokasi |  | Refueling | Blasting Activity | Pindah Alat | Tunggu Alat Lain | Cek Ban | Tool Box | Hujan | Prestart | Makan | Cuaca (Basah, Kabut) |  | No Job | Lain-Lain |  | Service | Progress Repair | Waiting Part | Waiting Man Power | No Operator
1 | 03-Feb-2024 | 879 | 883 | 4 | 883 | 883 | 0 | Blade |  | Ahmad Subangkit | Pad A | m. novit | - | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 1 | 2 | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
2 | 06-Nov-2023 | 88 | 98 | 10 | 98 | 108 | 10 | Ripper |  | Bagus Mujiono | buttress | Ismail | Buttress | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
3 | 07-Nov-2023 | 108 | 117 | 9 | 117 | 117 | 0 | Ripper |  | Bagus Mujiono | buttress |  | Buttress | 9 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
4 | 12-Nov-2023 | 156 | 166 | 10 | 166 | 166 | 0 | Ripper |  | Bagus Mujiono | PAD B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0.42 | 0 | 1.42 | 12 | 0 | 12 | 0 | 0.58 | 0 | 0 | 0 | 0.58 | 97.58 | 24 | 0 | 42.7 | 0 | 0 | Add oil engine | 0
5 | 10-Nov-2023 | 137 | 146 | 9 | 146 | 146 | 0 | Ripper |  | Bagus Mujiono | bay 7 |  | bay 7 | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
6 | 08-Nov-2023 | 117 | 127 | 10 | 127 | 127 | 0 | Ripper |  | Bagus Mujiono | buttress |  | Buttress | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
7 | 13-Nov-2023 | 166 | 176 | 10 | 176 | 176 | 0 | Ripper |  | Bagus Mujiono | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
8 | 16-Nov-2023 | 195 | 205 | 10 | 205 | 205 | 0 | Ripper |  | Bagus Mujiono | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
9 | 17-Nov-2023 | 205 | 214 | 9 | 214 | 214 | 0 | Ripper |  | Bagus Mujiono | Pad B |  | Pad B | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
10 | 18-Nov-2023 | 214 | 224 | 10 | 224 | 224 | 0 | Ripper |  | Bagus Mujiono | PAD B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
11 | 14-Nov-2023 | 176 | 186 | 8.42 | 186 | 186 | 0 | Ripper |  | Bagus Mujiono | Pad B |  | Pad B | 8.42 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.58 | 0.5 | 1 | 0 | 3.58 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 35.08 | 1.58 | 1.58 | HUJAN | 0
12 | 15-Nov-2023 | 186 | 195 | 9 | 195 | 195 | 0 | Ripper |  | Bagus Mujiono | PAD B |  | Pad B | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
13 | 01-Nov-2023 | 8 | 18 | 10 | 18 | 27 | 8.83 | Ripper | On Hire | Dedi Setiawan | buttress | bagus mujiono | Buttress | 18.83 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 0 | 0 | 0 | 1.17 | 0 | 0 | 0 | 0 | 1.17 | 95.13 | 24 | 0 | 82.48 | 0.17 | 0 |  | 0.17 | tambah oli hydrolik
14 | 09-Nov-2023 | 127 | 137 | 10 | 137 | 137 | 0 | Ripper |  | Doni Agus | bay 7 |  | bay 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
15 | 11-Nov-2023 | 146 | 156 | 10 | 156 | 156 | 0 | Ripper |  | Doni Agus | Pad A |  | Pad A | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
16 | 26-Nov-2023 | 288 | 298 | 10 | 298 | 298 | 0 | Ripper |  | Edi Nurcholis | Lot 1 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
17 | 03-Dec-2023 | 349 | 359 | 10 | 359 | 359 | 0 | Ripper | Day Off | Edi Nurcholis | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
18 | 28-Nov-2023 | 308 | 318 | 10 | 318 | 318 | 0 | Blade |  | Edi Nurcholis | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
19 | 30-Nov-2023 | 328 | 337 | 9 | 337 | 337 | 0 | Ripper |  | Edi Nurcholis | pad C |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
20 | 22-Nov-2023 | 249 | 259 | 10 | 259 | 259 | 0 | Ripper |  | Edi Nurcholis | Bay 9 |  | Bay 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
21 | 24-Nov-2023 | 269 | 278 | 9 | 278 | 278 | 0 | Ripper |  | Edi Nurcholis | LOT 1 |  | Lot 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
22 | 23-Nov-2023 | 259 | 269 | 10 | 269 | 269 | 0 | Ripper |  | Edi Nurcholis | Bay 9 |  | Bay 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
23 | 25-Nov-2023 | 278 | 288 | 10 | 288 | 288 | 0 | Ripper |  | Edi Nurcholis | Lot 1 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
24 | 27-Nov-2023 | 298 | 308 | 10 | 308 | 308 | 0 | Ripper |  | Edi Nurcholis | melati |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
25 | 29-Nov-2023 | 318 | 328 | 10 | 328 | 328 | 0 | Ripper |  | Edi Nurcholis | pad C |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
26 | 01-Dec-2023 | 337 | 346 | 9 | 346 | 346 | 0 | Ripper |  | Edi Nurcholis | pad C |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
27 | 19-Nov-2023 | 224 | 230 | 6 | 230 | 230 | 0 | Ripper | Day Off | Hari Sulistyo | Pad B |  | Pad B | 6 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 25 | 0 | 0 |  | 0
28 | 02-Dec-2023 | 346 | 349 | 2 | 349 | 349 | 0 | Ripper |  | Iklasul A'Mal | Pad C |  | PAD C | 2 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7 | 0.5 | 1 | 0 | 9 | 12 | 0 | 12 | 1 | 0 | 0 | 0 | 0 | 1 | 95.83 | 24 | 0 | 8.7 | 1 | 1 | unit can't start | 0
29 | 03-Nov-2023 | 44.5 | 51 | 6.5 | 51 | 60 | 9 | Ripper |  | Ismail | buttress | bagus mujiono | Buttress | 15.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 0 | 5 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 64.58 | 0 | 0 |  | 0
30 | 04-Nov-2023 | 60 | 70 | 10 | 70 | 80 | 10 | Ripper |  | Ismail | buttress | bagus mujiono | Buttress | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
31 | 02-Nov-2023 | 27 | 35 | 8 | 35 | 44.5 | 9.5 | Ripper |  | Ismail | Pad C | Winarso | Buttress | 17.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 97.92 | 24 | 0 | 74.47 | 0 | 0 |  | 0
32 | 05-Nov-2023 | 80 | 88 | 8 | 88 | 88 | 0 | Ripper | Day Off | Ismail | buttress |  | Buttress | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
33 | 20-Nov-2023 | 230 | 240 | 10 | 240 | 240 | 0 | Ripper |  | Ismail | Bay 9 |  | Bay 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
34 | 21-Nov-2023 | 240 | 249 | 9 | 249 | 249 | 0 | Ripper |  | Ismail | Bay 9 |  | Bay 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
35 | 02-Feb-2024 | 871 | 879 | 8 | 879 | 879 | 0 | Blade |  | m. novit | Interlift | bowo | - | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
36 | 04-Feb-2024 | 883 | 886 | 3 | 886 | 886 | 0 | Blade |  | m. novit | Lot 1 | ismail | - | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 1 | 2 | 0 | 11 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 12.5 | 0 | 0 |  | 0
37 | 07-Dec-2023 | 385 | 395 | 10 | 395 | 395 | 0 | Ripper |  | m. novit | Bay 7 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
38 | 08-Dec-2023 | 395 | 404 | 9 | 404 | 404 | 0 | Ripper |  | m. novit | Lot 1 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
39 | 16-Dec-2023 | 468 | 477 | 9 | 477 | 477 | 0 | Ripper |  | m. novit | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
40 | 19-Dec-2023 | 487 | 496.5 | 9.5 | 496.5 | 496.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 9.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12.5 | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 39.58 | 0 | 0 |  | 0
41 | 22-Dec-2023 | 516.5 | 525.5 | 9 | 525.5 | 525.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
42 | 25-Dec-2023 | 545.5 | 555.5 | 10 | 555.5 | 555.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
43 | 04-Dec-2023 | 359 | 366 | 7 | 366 | 366 | 0 | Ripper |  | m. novit | Interlift |  | - | 7 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3 | 0.5 | 1 | 0 | 5 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 |  | 0
44 | 06-Dec-2023 | 375 | 385 | 10 | 385 | 385 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
45 | 30-Jan-2024 | 843 | 852 | 9 | 852 | 852 | 0 | Blade |  | m. novit | Bay 6 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
46 | 05-Dec-2023 | 366 | 375 | 9 | 375 | 375 | 0 | Ripper |  | m. novit | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
47 | 09-Dec-2023 | 404 | 414 | 10 | 414 | 414 | 0 | Ripper |  | m. novit | Bay 8 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
48 | 12-Dec-2023 | 434 | 444 | 10 | 444 | 444 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
49 | 14-Dec-2023 | 454 | 464 | 9.5 | 464 | 464 | 0 | Ripper |  | m. novit | Interlift |  | - | 9.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 0 | 2.5 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 39.58 | 0.5 | 0.5 | hujan | 0
50 | 13-Dec-2023 | 444 | 454 | 10 | 454 | 454 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
51 | 24-Dec-2023 | 535.5 | 545.5 | 10 | 545.5 | 545.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
52 | 30-Dec-2023 | 589.25 | 593.25 | 4 | 593.25 | 593.25 | 0 | Ripper |  | m. novit | Interlift |  | - | 4 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 6 | 8 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
53 | 10-Dec-2023 | 414 | 424 | 10 | 424 | 424 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
54 | 28-Dec-2023 | 575.25 | 585.25 | 10 | 585.25 | 585.25 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
55 | 15-Dec-2023 | 464 | 468 | 4 | 468 | 468 | 0 | Ripper |  | m. novit | pad C |  | - | 4 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6 | 0.5 | 1 | 0 | 8 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
56 | 27-Dec-2023 | 565.25 | 575.25 | 10 | 575.25 | 575.25 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
57 | 18-Dec-2023 | 477 | 487 | 10 | 487 | 487 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
58 | 20-Dec-2023 | 496.5 | 506.5 | 10 | 506.5 | 506.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
59 | 21-Dec-2023 | 506.5 | 516.5 | 10 | 516.5 | 516.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
60 | 27-Jan-2024 | 825 | 833 | 8 | 833 | 833 | 0 | Blade |  | m. novit | Interlift |  | - | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
61 | 29-Jan-2024 | 833 | 843 | 10 | 843 | 843 | 0 | Blade |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
62 | 31-Jan-2024 | 852 | 862 | 10 | 862 | 862 | 0 | Blade |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
63 | 01-Feb-2024 | 862 | 871 | 8.5 | 871 | 871 | 0 | Blade |  | m. novit | Interlift |  | - | 8.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 97.92 | 24 | 0 | 36.17 | 0.5 | 0.5 | Ac problem | 0
64 | 23-Dec-2023 | 525.5 | 535.5 | 10 | 535.5 | 535.5 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
65 | 11-Dec-2023 | 424 | 434 | 10 | 434 | 434 | 0 | Ripper |  | m. novit | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
66 | 02-Jan-2024 | 593.25 | 602.25 | 9 | 602.25 | 602.25 | 0 | Ripper |  | m. novit | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
67 | 06-Jan-2024 | 630.25 | 636.25 | 6 | 636.25 | 636.25 | 0 | Blade |  | M NOVIT | PAD B |  | - | 6 | 0 | 0 | 0 | 0 | 0 | 0.5 | 16 | 0.5 | 1 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 25 | 0 | 0 |  | 0
68 | 26-Jan-2024 | 817 | 825 | 8 | 825 | 825 | 0 | Blade |  | M NOVIT | Interlift |  | - | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 14 | 0.5 | 1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
69 | 04-Jan-2024 | 612.25 | 621.25 | 9 | 621.25 | 621.25 | 0 | Blade |  | M NOVIT | PAD B |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
70 | 24-Jan-2024 | 797 | 807 | 10 | 807 | 807 | 0 | Blade |  | M NOVIT | BAY 7 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
71 | 23-Jan-2024 | 788 | 797 | 9 | 797 | 797 | 0 | Blade |  | M NOVIT | BAY 6 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
72 | 25-Jan-2024 | 807 | 817 | 10 | 817 | 817 | 0 | Blade |  | M NOVIT | BAY 3 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
73 | 22-Jan-2024 | 778 | 788 | 10 | 788 | 788 | 0 | Blade |  | M NOVIT | BAY 5 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
74 | 26-Dec-2023 | 555.5 | 565.25 | 9.75 | 565.25 | 565.25 | 0 | Ripper |  | M.NOVIT | Interlift |  | - | 9.75 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.5 | 1 | 0 | 2.25 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 40.63 | 0 | 0 |  | 0
75 | 15-Jan-2024 | 712 | 722 | 10 | 722 | 722 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
76 | 29-Dec-2023 | 585.25 | 589.25 | 4 | 589.25 | 589.25 | 0 | Ripper |  | Muhammad Novit | Pad C |  | PAD C | 4 | 0 | 0 | 0 | 0 | 0 | 0.5 | 17 | 0.5 | 2 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
77 | 17-Jan-2024 | 731 | 740 | 9 | 740 | 740 | 0 | Blade |  | Muhammad Novit | Dam 5 |  | Dam 5 | 9 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
78 | 18-Jan-2024 | 740 | 750 | 10 | 750 | 750 | 0 | Blade |  | Muhammad Novit | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
79 | 31-Dec-2023 | 593.25 | 593.25 | 0 | 593.25 | 593.25 | 0 | Ripper |  | Muhammad Novit | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
80 | 09-Jan-2024 | 654 | 664 | 10 | 664 | 664 | 0 | Blade |  | Muhammad Novit | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
81 | 10-Jan-2024 | 664 | 674 | 10 | 674 | 674 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
82 | 13-Jan-2024 | 693 | 703 | 10 | 703 | 703 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
83 | 14-Jan-2024 | 703 | 712 | 9 | 712 | 712 | 0 | Blade | dAY oFF | Muhammad Novit | Dam 5 |  | Dam 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
84 | 08-Jan-2024 | 644 | 654 | 10 | 654 | 654 | 0 | Blade |  | Muhammad Novit | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
85 | 16-Jan-2024 | 722 | 731 | 9 | 731 | 731 | 0 | Blade |  | Muhammad Novit | Pad C |  | PAD C | 9 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
86 | 19-Jan-2024 | 750 | 758 | 8 | 758 | 758 | 0 | Blade |  | Muhammad Novit | Pad C |  | PAD C | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 2 | 0 | 4 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
87 | 20-Jan-2024 | 758 | 768 | 10 | 768 | 768 | 0 | Blade |  | Muhammad Novit | PAD B |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
88 | 12-Jan-2024 | 684 | 693 | 9 | 693 | 693 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
89 | 07-Jan-2024 | 636.25 | 644 | 7.75 | 644 | 644 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 7.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 2.25 | 0.5 | 1 | 0 | 4.25 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 32.29 | 0 | 0 |  | 0
90 | 11-Jan-2024 | 674 | 684 | 10 | 684 | 684 | 0 | Blade |  | Muhammad Novit | Pad B |  | Pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
91 | 21-Jan-2024 | 768 | 778 | 10 | 778 | 778 | 0 | Blade |  | NOVIT | PAD B |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
92 | 05-Jan-2024 | 621.25 | 630.25 | 9 | 630.25 | 630.25 | 0 | Blade |  | NOVIT | LOT 1 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
93 | 03-Jan-2024 | 602.25 | 612.25 | 10 | 612.25 | 612.25 | 0 | RIPPER |  | NOVIT | PAD B |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
94 | 19-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Perjalanan Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
95 | 31-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
96 | 30-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
97 | 29-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
98 | 28-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
99 | 27-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
100 | 26-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
101 | 25-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
102 | 22-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Perjalanan Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
103 | 24-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Prepare Komisioning |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
104 | 23-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Perjalanan Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
105 | 17-Dec-2023 | 477 | 477 | 0 | 477 | 477 | 0 | Ripper | Day Off |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
106 | 01-Jan-2024 | 593.25 | 593.25 | 0 | 593.25 | 593.25 | 0 | Ripper | Day Off |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
107 | 20-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Perjalanan Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
108 | 28-Jan-2024 | 833 | 833 | 0 | 833 | 833 | 0 | Blade | Day Off |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
109 | 21-Oct-2023 | 8 | 8 | 0 | 8 | 8 | 0 | Ripper | Perjalanan Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
TOTAL |  |  |  | 826.92 |  |  | 47.33 | [6 empty] | 874.25 | 0 | 0 | 0 | 0 | 0 | 53.25 | 109.33 | 50 | 104.42 | 0 | 323 | 1103 | 312 | 1415 | 2.17 | 1.08 | 0 | 0 | 0.5 | 3.75 | 99.8567 | 2616 | 0 | 33.4915 | 3.75 | 3.58 |  | 0.17
| Prepared by, |  |  | Acknowledge by, |  |  | Checked by, |  |  | Approved by,
| Name: |  |  | Name: |  |  | Name: |  |  | Name:
| Position: |  |  | Position: |  |  | Position: |  |  | Position:
| Date: |  |  | Date: |  |  | Date: |  |  | Date: