## CP 12
Record of HM
Equipment |  |  | : | Vibro Compactor
Specification |  |  | : | BOMAG, BW211D-40
UA Asset Number |  |  | : | CP1069
User Number |  |  | : | CP 12
Attachment Name |  |  | : | BUCKET, PAD FOOT, PADFOOT,
User |  |  | : | PT. BUMI SUKSESINDO
Location |  |  | : | BANYUWANGI
Periode |  |  | : | 10 October 2023 s/d 25 January 2024 = 108 Hari
No. | Date | Hours Meter (HM) | [5 empty] | Attachment Name | Remark | Day |  | Night |  | Total HM | Delay | [9 empty] | Total Delay | IDLE |  | Total Idle | BREAKDOWN |  |  |  |  | Total Breakdown | PA(%) | Total All | Check | UA(%) | DEDUCTION | Day Shift |  | Night Shift
|  | Day Start | Day Finish | Total Shift 1 | Night Start | Night Finish | Total Shift 2 |  |  | Operator | Lokasi | Operator | Lokasi |  | Refueling | Blasting Activity | Pindah Alat | Tunggu Alat Lain | Cek Ban | Tool Box | Hujan | Prestart | Makan | Cuaca (Basah, Kabut) |  | No Job | Lain-Lain |  | Service | Progress Repair | Waiting Part | Waiting Man Power | No Operator
1 | 10-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
2 | 11-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
3 | 12-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
4 | 13-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
5 | 14-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Bucket | Mobilisasi |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
6 | 15-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
7 | 16-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
8 | 17-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
9 | 18-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
10 | 19-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
11 | 20-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
12 | 21-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
13 | 22-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
14 | 23-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
15 | 24-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
16 | 25-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Bucket | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
17 | 26-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6503 | 0 | Padfoot | Prepare commisioning |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
18 | 27-Oct-2023 | 6503 | 6503 | 0 | 6503 | 6507 | 4 | Padfoot | Backup CP 02 |  | - | Slamet Agung S | pad B | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
19 | 28-Oct-2023 | 6507 | 6507 | 0 | 6507 | 6517 | 10 | Padfoot | Backup CP 02 |  | - | Slamet Agung S | pad B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
20 | 29-Oct-2023 | 6517 | 6520 | 2.6 | 6520 | 6529 | 8.42 | Padfoot | Backup CP 06 | Rizal Azizi | Lot 1 | Tomas | Lot 1 | 11.02 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 7 | 0 | 7 | 0 | 1.98 | 0 | 0 | 0 | 1.98 | 91.75 | 24 | 0 | 50.05 | 0.98 | 0.4 | AC Problem | 0.58 | AC Problem
21 | 30-Oct-2023 | 6529 | 6538 | 9 | 6538 | 6548 | 10 | Padfoot | Backup CP 06 | Iwan | Lot 1 | Tomas | Lot 1 | 19 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 79.17 | 0 | 0 |  | 0
22 | 31-Oct-2023 | 6548 | 6548 | 0 | 6548 | 6548 | 0 | Padfoot | Standby |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
23 | 01-Nov-2023 | 6548 | 6555 | 7 | 6555 | 6564 | 8.33 | Padfoot | On hire | Rizal Azizi | RL126 | Taufik | RL126 | 15.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 2.9 | 0 | 2.9 | 0 | 1.77 | 0 | 0 | 0 | 1.77 | 92.63 | 24 | 0 | 68.96 | 0.67 | 0 |  | 0.67 | Mati mendadak
24 | 02-Nov-2023 | 6564 | 6574 | 10 | 6574 | 6584 | 10 | Padfoot |  | Ahmad Subangkit | RL126 | Aris Budi | RL126 | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
25 | 03-Nov-2023 | 6584 | 6593 | 9 | 6593 | 6603 | 10 | Padfoot |  | Ahmad Subangkit | Interlift | Aris Budi | Interlift | 19 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 79.17 | 0 | 0 |  | 0
26 | 04-Nov-2023 | 6603 | 6613 | 10 | 6613 | 6623 | 10 | Padfoot |  | Ahmad Subangkit | Interlift | Forry bassidika | Interlift | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
27 | 05-Nov-2023 | 6623 | 6623 | 0 | 6623 | 6623 | 0 | Padfoot | Day off |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
28 | 06-Nov-2023 | 6623 | 6632 | 8.3 | 6632 | 6632 | 0 | Padfoot |  | Forry Bassidika | Bay 7 |  | - | 8.3 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12.02 | 0 | 12.02 | 0 | 1.68 | 0 | 0 | 0 | 1.68 | 93 | 24 | 0 | 37.19 | 0.7 | 0.7 | Service penambahan | 0
29 | 07-Nov-2023 | 6632 | 6641 | 9 | 6641 | 6641 | 0 | Padfoot |  | basofi | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
30 | 08-Nov-2023 | 6641 | 6651 | 10 | 6651 | 6651 | 0 | Padfoot |  | basofi | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
31 | 09-Nov-2023 | 6651 | 6661 | 10 | 6661 | 6661 | 0 | Padfoot |  | basofi | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 50 | 24 | 0 | 83.33 | 0 | 0 |  | 0
32 | 10-Nov-2023 | 6661 | 6670 | 9 | 6670 | 6670 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
33 | 11-Nov-2023 | 6670 | 6680 | 10 | 6680 | 6680 | 0 | Padfoot |  | Forry Bassidika/ | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
34 | 12-Nov-2023 | 6680 | 6689 | 9 | 6689 | 6689 | 0 | Padfoot |  | Forry Bassidika/Aris | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
35 | 13-Nov-2023 | 6689 | 6698 | 9 | 6698 | 6698 | 0 | Padfoot |  | aris budi | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
36 | 14-Nov-2023 | 6698 | 6706 | 8 | 6706 | 6706 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
37 | 15-Nov-2023 | 6706 | 6715 | 8.17 | 6715 | 6715 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 8.17 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 1.83 | 0 | 0 | 0 | 1.83 | 92.38 | 24 | 0 | 36.85 | 0.83 | 0.83 | unit cant start | 0
38 | 16-Nov-2023 | 6715 | 6725 | 10 | 6725 | 6725 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
39 | 17-Nov-2023 | 6725 | 6734 | 9 | 6734 | 6734 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
40 | 18-Nov-2023 | 6734 | 6744 | 10 | 6744 | 6744 | 0 | Padfoot |  | Forry Bassidika | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
41 | 19-Nov-2023 | 6744 | 6744 | 0 | 6744 | 6744 | 0 | Padfoot | Day off |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
42 | 20-Nov-2023 | 6744 | 6754 | 10 | 6754 | 6754 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
43 | 21-Nov-2023 | 6754 | 6763 | 9 | 6763 | 6763 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
44 | 22-Nov-2023 | 6763 | 6772 | 8.87 | 6772 | 6772 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 8.87 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12.13 | 0 | 12.13 | 0 | 1 | 0 | 0 | 0 | 1 | 95.83 | 24 | 0 | 38.57 | 0.13 | 0.13 | Drum Problem | 0
45 | 23-Nov-2023 | 6772 | 6781 | 8.42 | 6781 | 6781 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 8.42 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 1.58 | 0 | 0 | 0 | 1.58 | 93.42 | 24 | 0 | 37.56 | 0.58 | 0.58 | unit can't start | 0
46 | 24-Nov-2023 | 6781 | 6788 | 7 | 6788 | 6788 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 7 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 14 | 0 | 14 | 0 | 1 | 0 | 0 | 0 | 1 | 95.83 | 24 | 0 | 30.43 | 0 | 0 |  | 0
47 | 25-Nov-2023 | 6788 | 6796 | 6.83 | 6796 | 6796 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 6.83 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 3.17 | 0 | 0 | 0 | 3.17 | 86.79 | 24 | 0 | 32.79 | 1.17 | 1.17 | repair adjuster selenoid gas | 0
48 | 26-Nov-2023 | 6796 | 6806 | 10 | 6806 | 6806 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
49 | 27-Nov-2023 | 6806 | 6816 | 10 | 6816 | 6818 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 2 | 0 |  | 2 | low power-adjust and repair gs selenoid
50 | 28-Nov-2023 | 6818 | 6828 | 10 | 6828 | 6828 | 0 | Pad Foot |  | Abdul Haris | Candrian |  | candrian | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
51 | 29-Nov-2023 | 6828 | 6835 | 7 | 6835 | 6835 | 0 | Padfoot |  | Abdul Haris | Candrian |  | - | 7 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 |  | 0
52 | 30-Nov-2023 | 6835 | 6842 | 6.45 | 6842 | 6842 | 0 | Padfoot |  | iwan pratama/abdul haris | Lot 1 |  | - | 6.45 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 8.55 | 0 | 8.55 | 2 | 5 | 0 | 0 | 0 | 7 | 70.83 | 24 | 0 | 37.94 | 0.55 | 0.55 | low power | 0
53 | 01-Dec-2023 | 6842 | 6847 | 5 | 6847 | 6847 | 0 | Padfoot |  | Abdul Haris | Bay 7 |  | - | 5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 5 | 0 | 0 | 0 | 5 | 79.17 | 24 | 0 | 26.32 | 0 | 0 |  | 0
54 | 02-Dec-2023 | 6847 | 6847 | 0 | 6847 | 6847 | 0 | Pad Foot | Breakdown |  | worksop |  | worksop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 |  | 0
55 | 03-Dec-2023 | 6847 | 6847 | 0 | 6847 | 6847 | 0 | Pad Foot | Day Off |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
56 | 04-Dec-2023 | 6847 | 6847 | 0 | 6847 | 6847 | 0 | Pad Foot |  | Aris Budi | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
57 | 05-Dec-2023 | 6847 | 6854 | 7 | 6854 | 6854 | 0 | Pad Foot |  | Aris Budi | Pad C |  | PAD C | 7 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2 | 0.5 | 1 | 0 | 5 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 |  | 0
58 | 06-Dec-2023 | 6854 | 6864 | 9.38 | 6864 | 6864 | 0 | Pad Foot |  | aris budi k | Interlift |  | - | 9.38 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0.62 | 0 | 0 | 0 | 0.62 | 97.42 | 24 | 0 | 40.12 | 0.62 | 0.62 | hose hyrolik leaking | 0
59 | 07-Dec-2023 | 6864 | 6874 | 10 | 6874 | 6874 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
60 | 08-Dec-2023 | 6874 | 6883 | 9 | 6883 | 6883 | 0 | Padfoot |  | aris budi k | Candrian |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
61 | 09-Dec-2023 | 6883 | 6893 | 10 | 6893 | 6893 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
62 | 10-Dec-2023 | 6893 | 6903 | 10 | 6903 | 6903 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
63 | 11-Dec-2023 | 6903 | 6913 | 10 | 6913 | 6913 | 0 | Padfoot |  | aris budi k | Lot 1 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
64 | 12-Dec-2023 | 6913 | 6923 | 10 | 6923 | 6923 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
65 | 13-Dec-2023 | 6923 | 6933 | 10 | 6933 | 6933 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
66 | 14-Dec-2023 | 6933 | 6942 | 9 | 6942 | 6942 | 0 | Padfoot |  | aris budi k | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
67 | 15-Dec-2023 | 6942 | 6945 | 3 | 6945 | 6945 | 0 | Padfoot |  | aris budi k | pad C |  | - | 3 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7 | 0.5 | 1 | 0 | 9 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 12.5 | 0 | 0 |  | 0
68 | 16-Dec-2023 | 6945 | 6945 | 0 | 6945 | 6945 | 0 | Pad Foot |  |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
69 | 17-Dec-2023 | 6945 | 6945 | 0 | 6945 | 6945 | 0 | Pad Foot | Day Off |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
70 | 18-Dec-2023 | 6945 | 6955 | 10 | 6955 | 6955 | 0 | Pad Foot |  | Abdul Haris | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
71 | 19-Dec-2023 | 6955 | 6964 | 9 | 6964 | 6964 | 0 | Pad Foot |  | Abdul Haris | Pad C |  | PAD C | 9 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
72 | 20-Dec-2023 | 6964 | 6974 | 10 | 6974 | 6974 | 0 | Padfoot |  | Abdul Haris | Dam 5 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
73 | 21-Dec-2023 | 6974 | 6984 | 10 | 6984 | 6984 | 0 | Padfoot |  | Abdul Haris | Lot 1 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
74 | 22-Dec-2023 | 6984 | 6993 | 9 | 6993 | 6993 | 0 | Padfoot |  | Abdul Haris | Lot 1 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
75 | 23-Dec-2023 | 6993 | 7003 | 10 | 7003 | 7003 | 0 | Padfoot |  | Abdul Haris | Lot 1 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
76 | 24-Dec-2023 | 7003 | 7013 | 10 | 7013 | 7013 | 0 | Padfoot |  | Abdul Haris | pad C |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
77 | 25-Dec-2023 | 7013 | 7023 | 10 | 7023 | 7023 | 0 | Padfoot |  | ROHMAN HUDI | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
78 | 26-Dec-2023 | 7023 | 7032.75 | 9.75 | 7032.75 | 7032.75 | 0 | Pad foot |  | ABDUL HARIS | Interlift |  | - | 9.75 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.5 | 1 | 0 | 2.25 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 40.63 | 0 | 0 |  | 0
79 | 27-Dec-2023 | 7032.75 | 7042.75 | 10 | 7042.75 | 7042.75 | 0 | Padfoot |  | Abdul Haris | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
80 | 28-Dec-2023 | 7042.75 | 7052.75 | 10 | 7052.75 | 7052.75 | 0 | Padfoot |  | Abdul Haris | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
81 | 29-Dec-2023 | 7052.75 | 7052.75 | 0 | 7052.75 | 7052.75 | 0 | Pad Foot |  | Abdul Haris | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
82 | 30-Dec-2023 | 7052.75 | 7056.75 | 4 | 7056.75 | 7056.75 | 0 | Padfoot |  | Abdul Haris | Dam 5 |  | - | 4 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6 | 0.5 | 1 | 0 | 8 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
83 | 31-Dec-2023 | 7056.75 | 7056.75 | 0 | 7056.75 | 7056.75 | 0 | Pad Foot |  | Abdul Haris | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
84 | 01-Jan-2024 | 7056.75 | 7056.75 | 0 | 7056.75 | 7056.75 | 0 | Pad Foot | Day Off |  | Pad C |  | PAD C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
85 | 02-Jan-2024 | 7056.75 | 7066.25 | 8.88 | 7066.25 | 7066.25 | 0 | Padfoot |  | Forry Bassidika | Dam 5 |  | - | 8.88 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 1.12 | 0 | 0 | 0 | 1.12 | 95.33 | 24 | 0 | 38.81 | 0.62 | 0.62 | unit cant start | 0
86 | 03-Jan-2024 | 7066.25 | 7076.25 | 9 | 7076.25 | 7076.25 | 0 | Pad foot |  | FORRY B | Interlift |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 1 | 0 | 0 | 0 | 1 | 95.83 | 24 | 0 | 39.13 | 1 | 1 | unit cant start | 0
87 | 04-Jan-2024 | 7076.25 | 7086.25 | 10 | 7086.25 | 7086.25 | 0 | Pad foot |  | FORRY B | Interlift |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
88 | 05-Jan-2024 | 7086.25 | 7095.25 | 9 | 7095.25 | 7095.25 | 0 | Pad foot |  | FORRY B | LOT 1 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
89 | 06-Jan-2024 | 7095.25 | 7101 | 5.75 | 7101 | 7101 | 0 | Pad foot |  | FORRY B | PAD B |  | - | 5.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 16.25 | 0.5 | 1 | 0 | 18.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 23.96 | 0 | 0 |  | 0
90 | 07-Jan-2024 | 7101 | 7111 | 8 | 7111 | 7111 | 0 | Pad Foot |  | Forry Bassidika | Interlift |  | Interlift | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 2 | 91.67 | 24 | 0 | 36.36 | 2 | 2 | Ac problem | 0
91 | 08-Jan-2024 | 7111 | 7121 | 10 | 7121 | 7121 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
92 | 09-Jan-2024 | 7121 | 7131 | 10 | 7131 | 7131 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
93 | 10-Jan-2024 | 7131 | 7141 | 10 | 7141 | 7141 | 0 | Pad foot |  | Forry Bassidika | Pad C |  | PAD C | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
94 | 11-Jan-2024 | 7141 | 7151 | 10 | 7151 | 7151 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
95 | 12-Jan-2024 | 7151 | 7160 | 9 | 7160 | 7160 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
96 | 13-Jan-2024 | 7160 | 7170 | 10 | 7170 | 7170 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
97 | 14-Jan-2024 | 7170 | 7170 | 0 | 7170 | 7170 | 0 | Pad Foot | Day Off |  | Dam 5 |  | Dam 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
98 | 15-Jan-2024 | 7170 | 7180 | 10 | 7180 | 7180 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
99 | 16-Jan-2024 | 7180 | 7189 | 9 | 7189 | 7189 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 9 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0.5 | 1 | 0 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
100 | 17-Jan-2024 | 7189 | 7197 | 8 | 7197 | 7197 | 0 | Pad Foot |  | Forry Bassidika | Dam 5 |  | Dam 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 2 | 0.5 | 1 | 0 | 4 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 33.33 | 0 | 0 |  | 0
101 | 18-Jan-2024 | 7197 | 7202 | 3.5 | 7202 | 7202 | 0 | Pad Foot |  | Forry Bassidika | Lot 1 |  | Lot 1 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 5 | 0.5 | 1 | 0 | 7 | 12 | 0 | 12 | 0 | 1.5 | 0 | 0 | 0 | 1.5 | 93.75 | 24 | 0 | 15.56 | 1.5 | 1.5 | Ac problem | 0
102 | 19-Jan-2024 | 7202 | 7202 | 0 | 7202 | 7202 | 0 | Pad Foot |  | Forry Bassidika | LOT 1 |  | lot 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
103 | 20-Jan-2024 | 7202 | 7206 | 2.5 | 7206 | 7206 | 0 | Pad Foot |  | Forry Bassidika | LOT 1 |  | lot 1 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6 | 0.5 | 1 | 0 | 8 | 12 | 0 | 12 | 0 | 1.5 | 0 | 0 | 0 | 1.5 | 93.75 | 24 | 0 | 11.11 | 1.5 | 1.5 | hose fuel leaking | 0
104 | 21-Jan-2024 | 7206 | 7216 | 9 | 7216 | 7216 | 0 | Pad foot |  | FORRY B | LOT 1 |  | - | 9 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 1 | 0 | 0 | 0 | 1 | 95.83 | 24 | 0 | 39.13 | 1 | 1 | hose fuel leaking | 0
105 | 22-Jan-2024 | 7216 | 7226 | 10 | 7226 | 7226 | 0 | Pad foot |  | IWAN P | PAD B |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
106 | 23-Jan-2024 | 7226 | 7236 | 9.5 | 7236 | 7236 | 0 | Pad foot |  | FORRY B | DAM 5 |  | - | 9.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 97.92 | 24 | 0 | 40.43 | 0.5 | 0.5 | perbaikan rotari | 0
107 | 24-Jan-2024 | 7236 | 7246 | 10 | 7246 | 7246 | 0 | Pad foot |  | FORRY B | PAD B |  | PAD B | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
108 | 25-Jan-2024 | 7246 | 7256 | 10 | 7256 | 7256 | 0 | Pad foot |  | FORRY B | DAM 5 |  | - | 10 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 2 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 41.67 | 0 | 0 |  | 0
TOTAL |  |  |  | 665.9 |  |  | 70.75 | [6 empty] | 736.65 | 0 | 0 | 0 | 0 | 0 | 44.75 | 129.25 | 41.5 | 84 | 0 | 299.5 | 1484.6 | 0 | 1484.6 | 16 | 55.25 | 0 | 0 | 0 | 71.25 | 97.2512 | 2592 | 0 | 29.2933 | 16.35 | 13.1 |  | 3.25
| Prepared by, |  |  | Acknowledge by, |  |  | Checked by, |  |  | Approved by,
| Name: |  |  | Name: |  |  | Name: |  |  | Name:
| Position: |  |  | Position: |  |  | Position: |  |  | Position:
| Date: |  |  | Date: |  |  | Date: |  |  | Date: