## EX 23
Record of HM
Equipment |  |  | : | Excavator
Specification |  |  | : | KOMATSU, HB365-1
UA Asset Number |  |  | : | EXH3001T
User Number |  |  | : | EX 23
Attachment Name |  |  | : | ASD, ASDASD, ASDASDASD, ASDDAS, ASDDSA, ASDDSASD, ASDSAD, ASDSADASD, ASDSD, BUCKET, DSADSAD, EX 23, SADSADSA,
User |  |  | : | PT. BUMI SUKSESINDO
Location |  |  | : | BANYUWANGI
Periode |  |  | : | 01 January 1970 s/d 01 January 1970 = 121 Days
No. | Date | Hours Meter (HM) | [5 empty] | Attachment Name | Remark | Day |  | Night |  | Total HM | Delay | [9 empty] | Total Delay | IDLE |  | Total Idle | BREAKDOWN |  |  |  |  | Total Breakdown | PA(%) | Total All | Check | UA(%) | DEDUCTION | Day Shift |  | Night Shift
|  | Day Start | Day Finish | Total Shift 1 | Night Start | Night Finish | Total Shift 2 |  |  | Operator | Lokasi | Operator | Lokasi |  | Refueling | Blasting Activity | Pindah Alat | Tunggu Alat Lain | Cek Ban | Tool Box | Hujan | Prestart | Makan | Cuaca (Basah, Kabut) |  | No Job | Lain-Lain |  | Service | Progress Repair | Waiting Part | Waiting Man Power | No Operator
1 | 13-Mar-2023 | 1458.5 | 1473.5 | 15 | 1473.5 | 1482.5 | 9 | asdasd | asdasd | Aang Harianto | asdasd | Aang Harianto | asdasd | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | sadasd | 0 | asdasd
2 | 16-Mar-2023 | 1512.5 | 1522.5 | 10 | 1522.5 | 1532.5 | 10 | asdsadasd | asdsad | Aang Harianto | asdasd | Aang Harianto | asdasd | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 83.33 | 24 | 0 | 100 | 0 | 0 | asdasd | 0 | asdasd
3 | 17-Mar-2023 | 1532.5 | 1542 | 9.5 | 1542 | 1552 | 10 | asdasdasd | asd | Aang Harianto | asd | Aang Harianto | asd | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 81.25 | 24 | 0 | 100 | 0 | 0 | asdasd | 0 | asdasd
4 | 18-Mar-2023 | 1552 | 1554 | 2 | 1554 | 1568 | 14 | asddsa | sadasd | Aang Harianto | asd | Aang Harianto | asdsad | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 66.67 | 24 | 0 | 100 | 0 | 0 | sadasd | 0 | asddsa
5 | 19-Mar-2023 | 1568 | 1578 | 10 | 1578 | 1592 | 14 | asdsad |  | Aang Harianto | asd | Aang Harianto | dsa | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | asdasd | 0
6 | 20-Mar-2023 | 1592 | 1602 | 10 | 1602 | 1616 | 14 | asd | asdasd | Aang Harianto | asdsd | Aang Harianto | asdsad | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | sadsa | 0 | asdasd
7 | 22-Mar-2023 | 1616 | 1628 | 12 | 1628 | 1638 | 8 | asddsasd | asdasd | Aang Harianto | asdsad | Aang Harianto | asdasd | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 83.33 | 24 | 0 | 100 | 2 | 0 | asd | 2 | asdasd
8 | 23-Mar-2023 | 1638 | 1656 | 18 | 1656 | 1662 | 6 | dsadsad | asdsad | Aang Harianto | asdasd | Aang Harianto | asdasd | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | asdasd | 0 | asdasd
9 | 24-Mar-2023 | 1662 | 1676 | 14 | 1676 | 1686 | 10 | asddas | asdad | Aang Harianto | asdsda | Aang Harianto | asdasd | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | asdasd | 0 | asdsad
10 | 25-Mar-2023 | 1686 | 1696 | 10 | 1696 | 1706 | 10 | asdasd | asdasd | Aang Harianto | asdsad | Aang Harianto | asdasd | 20 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 | asdasd | 0 | asdasd
11 | 26-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | dsa | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
12 | 26-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
13 | 27-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
14 | 28-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
15 | 29-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
16 | 30-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
17 | 31-Mar-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
18 | 01-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
19 | 02-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
20 | 03-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
21 | 04-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
22 | 05-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
23 | 06-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
24 | 07-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
25 | 08-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
26 | 09-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
27 | 10-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
28 | 11-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
29 | 12-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
30 | 13-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
31 | 14-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
32 | 15-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
33 | 16-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
34 | 17-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
35 | 18-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
36 | 19-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
37 | 20-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
38 | 21-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
39 | 22-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
40 | 23-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
41 | 24-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
42 | 25-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
43 | 26-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
44 | 27-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
45 | 28-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
46 | 29-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
47 | 30-Apr-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
48 | 01-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
49 | 02-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
50 | 03-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
51 | 04-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
52 | 05-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
53 | 06-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
54 | 07-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
55 | 08-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
56 | 09-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
57 | 10-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
58 | 11-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
59 | 12-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
60 | 13-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
61 | 14-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
62 | 15-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
63 | 16-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
64 | 17-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
65 | 18-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
66 | 19-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
67 | 20-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
68 | 21-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
69 | 22-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
70 | 23-May-2023 | 1706 | 1706 | 0 | 1706 | 1706 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
71 | 24-May-2023 | 1706 | 1706 | 0 | 1706 | 1709 | 3 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 3 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 12.5 | 0 | 0 | asd | 0
72 | 25-May-2023 | 1709 | 1712 | 1 | 1709 | 1710 | 0 | EX 23 |  | Aang Harianto | asd | Aang Harianto | asd | 1 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 21 | 0 | 4 | 3 | 2 | sad | 1 | sda
73 | 26-May-2023 | 1710 | 1710 | 0 | 1710 | 1710 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
74 | 14-Mar-2023 | 1482.5 | 1492.5 | 10 | 1492.5 | 1502.5 | 10 | sadsadsa | asdsad | Abdul Halim | asdsad | Abdul Halim | asdasd | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 83.33 | 24 | 0 | 100 | 0 | 0 | asdsad | 0 | asdsad
75 | 15-Mar-2023 | 1502.5 | 1502.5 | 0 | 1502.5 | 1512.5 | 10 | asd | asdasd | Abdul Halim | asdsad |  | asdsad | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | 41.67 | 24 | 0 | 100 | 0 | 0 | asd | 0 | asdsad
76 | 13-Feb-2023 | 1119.5 | 1120.5 | 1 | 1120.5 | 1120.5 | 0 | Bucket |  | Abdurrohman | Stage 4 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0.25 | 21.5 | 0.25 | 1 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 4.17 | 0 | 0 |  | 0
77 | 14-Feb-2023 | 1120.5 | 1124.5 | 4 | 1124.5 | 1124.5 | 0 | Bucket |  | Abdurrohman | Stage 4 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0.25 | 18.5 | 0.25 | 1 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 16.67 | 0 | 0 |  | 0
78 | 16-Feb-2023 | 1124.5 | 1130 | 5.5 | 1130 | 1139.5 | 9.5 | Bucket |  | Abdurrohman | Stage 4 | Edi Purnomo | Stage 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6 | 0.5 | 2 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 62.5 | 0 | 0 |  | 0
79 | 17-Feb-2023 | 1139.5 | 1143.5 | 4 | 1143.5 | 1153.5 | 10 | Bucket |  | Abdurrohman | Stage 4 | Edi Purnomo | Stage 4 | 14 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7 | 0.5 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 58.33 | 0 | 0 |  | 0
80 | 18-Feb-2023 | 1153.5 | 1159.5 | 6 | 1159.5 | 1164.5 | 5 | Bucket |  | Abdurrohman | Stage 4 | Edi Purnomo | Stage 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0.5 | 10 | 0.5 | 2 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 45.83 | 0 | 0 |  | 0
81 | 19-Feb-2023 | 1164.5 | 1168.5 | 4 | 1168.5 | 1177 | 8.5 | Bucket |  | Abdurrohman | Stage 4 | Edi Purnomo | Stage 4 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 8.5 | 0.5 | 2 | 0 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 52.08 | 0 | 0 |  | 0
82 | 20-Feb-2023 | 1177 | 1186.5 | 9.5 | 1186.5 | 1197 | 10.5 | Bucket |  | Abdurrohman | Lot 1 | Edi Purnomo | Stage 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
83 | 21-Feb-2023 | 1197 | 1207.5 | 10.5 | 1207.5 | 1218 | 10.5 | Bucket |  | Abdurrohman | Lot 1 | Edi Purnomo | Lot 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 87.5 | 0 | 0 |  | 0
84 | 22-Feb-2023 | 1218 | 1228.5 | 10.5 | 1228.5 | 1239 | 10.5 | Bucket |  | Abdurrohman | Lot 1 | Edi Purnomo | Lot 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 87.5 | 0 | 0 |  | 0
85 | 23-Feb-2023 | 1239 | 1248.5 | 9.5 | 1248.5 | 1248.5 | 0 | Bucket |  | Abdurrohman | Stage 4 | Edi Purnomo |  | 9.5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 13 | 0.25 | 1 | 0 | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 39.58 | 0 | 0 |  | 0
86 | 25-Feb-2023 | 1248.5 | 1255.5 | 7 | 1255.5 | 1271.5 | 16 | EX 23 |  | Abdurrohman | Pad C | Edi Purnomo | asdsad | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 95.83 | 0 | 0 |  | 0
87 | 26-Jan-2023 | 993 | 1010 | 17 | 1010 | 1017 | 7 | Bucket | asd | Edi Purnomo | Dam 5 | Abdurrohman | Dam 5 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 0 | sad | 0 | asd
88 | 28-Jan-2023 | 1017 | 1023 | 6 | 1023 | 1023 | 0 | Bucket |  | Edi Purnomo | Dam 5 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0.25 | 4.5 | 0.25 | 1 | 0 | 6 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 25 | 0 | 0 |  | 0
89 | 30-Jan-2023 | 1023 | 1030.5 | 7.5 | 1030.5 | 1040.5 | 10 | Bucket |  | Edi Purnomo | Dam 5 | Abdurrohman | Dam 5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3.5 | 0.5 | 2 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 72.92 | 0 | 0 |  | 0
90 | 31-Jan-2023 | 1040.5 | 1047.5 | 7 | 1047.5 | 1047.5 | 0 | Bucket |  | Edi Purnomo | Dam 5 |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0.25 | 15.5 | 0.25 | 1 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 |  | 0
91 | 01-Feb-2023 | 1047.5 | 1050 | 2.5 | 1050 | 1050 | 0 | Bucket |  | Edi Purnomo | Stage 4 |  |  | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 20 | 0.25 | 1 | 0 | 21.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 10.42 | 0 | 0 |  | 0
92 | 02-Feb-2023 | 1050 | 1051 | 1 | 1051 | 1053.5 | 2.5 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Stage 4 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 17.5 | 0.5 | 2 | 0 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 14.58 | 0 | 0 |  | 0
93 | 03-Feb-2023 | 1053.5 | 1056 | 2.5 | 1056 | 1066 | 10 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Dam 5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 8.5 | 0.5 | 2 | 0 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 52.08 | 0 | 0 |  | 0
94 | 04-Feb-2023 | 1066 | 1071.5 | 5.5 | 1071.5 | 1081.5 | 10 | Bucket |  | Edi Purnomo | Dam 5 | Abdurrohman | Dam 5 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 5.5 | 0.5 | 2 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 64.58 | 0 | 0 |  | 0
95 | 08-Feb-2023 | 1081.5 | 1089 | 7.5 | 1089 | 1094 | 5 | Bucket |  | Edi Purnomo | Pad B | Abdurrohman | Stage 4 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 8.5 | 0.5 | 2 | 0 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 52.08 | 0 | 0 |  | 0
96 | 09-Feb-2023 | 1094 | 1098 | 4 | 1098 | 1107.5 | 9.5 | Bucket |  | Edi Purnomo | Pad B | Abdurrohman | Stage 4 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7.5 | 0.5 | 2 | 0 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 56.25 | 0 | 0 |  | 0
97 | 10-Feb-2023 | 1107.5 | 1116.5 | 9 | 1116.5 | 1116.5 | 0 | Bucket |  | Edi Purnomo | Stage 4 |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0.25 | 13.5 | 0.25 | 1 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 37.5 | 0 | 0 |  | 0
98 | 11-Feb-2023 | 1116.5 | 1116.5 | 0 | 1116.5 | 1119.5 | 3 | Bucket |  | Edi Purnomo |  | Abdurrohman | Stage 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0.25 | 19.5 | 0.25 | 1 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 12.5 | 0 | 0 |  | 0
99 | 27-Feb-2023 | 1272.5 | 1279.5 | 7 | 1279.5 | 1279.5 | 0 | Bucket |  | Edi Purnomo | Pad C | Abdurrohman |  | 7 | 0 | 0 | 0 | 0 | 0 | 0.25 | 15.5 | 0.25 | 1 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 |  | 0
100 | 28-Feb-2023 | 1279.5 | 1284.5 | 5 | 1284.5 | 1284.5 | 0 | Bucket |  | Edi Purnomo | Dam 5 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 17.5 | 0.25 | 1 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 20.83 | 0 | 0 |  | 0
101 | 01-Mar-2023 | 1284.5 | 1288 | 3.5 | 1288 | 1293 | 5 | Bucket |  | Edi Purnomo | Pad C | Abdurrohman | PAD C | 8.5 | 1 | 1 | 1 | 2 | 1 | 0.5 | 0.5 | 0.5 | 2 | 0 | 9.5 | 3 | 1 | 4 | 0 | 1 | 0 | 1 | 0 | 2 | 91.67 | 24 | 0 | 38.64 | 0 | 0 |  | 0
102 | 02-Mar-2023 | 1293 | 1303.5 | 10.5 | 1303.5 | 1314 | 10.5 | Bucket |  | Edi Purnomo | Pad C | Abdurrohman | PAD C | 21 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 87.5 | 0 | 0 |  | 0
103 | 03-Mar-2023 | 1314 | 1323.5 | 9.5 | 1323.5 | 1334 | 10.5 | Bucket |  | Edi Purnomo | Pad C | Abdurrohman | PAD C | 20 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 0 | 0 |  | 0
104 | 04-Mar-2023 | 1334 | 1344.5 | 10.5 | 1344.5 | 1349.5 | 5 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Stage 4 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 5.5 | 0.5 | 2 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 64.58 | 0 | 0 |  | 0
105 | 05-Mar-2023 | 1349.5 | 1352.5 | 3 | 1352.5 | 1361.5 | 9 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Stage 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0.5 | 9 | 0.5 | 2 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 50 | 0 | 0 |  | 0
106 | 06-Mar-2023 | 1361.5 | 1368.5 | 7 | 1368.5 | 1378.5 | 10 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Stage 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0.5 | 4 | 0.5 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 70.83 | 0 | 0 |  | 0
107 | 07-Mar-2023 | 1378.5 | 1389 | 10.5 | 1389 | 1399.5 | 10.5 | Bucket |  | Edi Purnomo | Stage 4 | Abdurrohman | Stage 4 | 21 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 87.5 | 0 | 0 |  | 0
108 | 08-Mar-2023 | 1399.5 | 1405.5 | 6 | 1405.5 | 1405.5 | 0 | Bucket |  | Edi Purnomo | Stage 4 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 1 | 0 | 1.5 | 16.5 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 25 | 0 | 0 |  | 0
109 | 27-Jan-2023 | 1017 | 1017 | 0 | 1017 | 1017 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
110 | 29-Jan-2023 | 1023 | 1023 | 0 | 1023 | 1023 | 0 | Bucket | Day Off |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
111 | 05-Feb-2023 | 1081.5 | 1081.5 | 0 | 1081.5 | 1081.5 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
112 | 06-Feb-2023 | 1081.5 | 1081.5 | 0 | 1081.5 | 1081.5 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
113 | 07-Feb-2023 | 1081.5 | 1081.5 | 0 | 1081.5 | 1081.5 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
114 | 12-Feb-2023 | 1119.5 | 1119.5 | 0 | 1119.5 | 1119.5 | 0 | Bucket | Day Off |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
115 | 15-Feb-2023 | 1124.5 | 1124.5 | 0 | 1124.5 | 1124.5 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
116 | 24-Feb-2023 | 1248.5 | 1248.5 | 0 | 1248.5 | 1248.5 | 0 | Bucket | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
117 | 26-Feb-2023 | 1272.5 | 1272.5 | 0 | 1272.5 | 1272.5 | 0 | Bucket | Day Off |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 0 |  | 0
118 | 09-Mar-2023 | 1417.5 | 1417.5 | 0 | 1417.5 | 1418.5 | 1 | EX 23 | Off Hire digantikan dengan EX20 |  | asd |  | asd | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 0 | 2 | 0 | 0 | 0 | 2 | 91.67 | 24 | 0 | 4.55 | 0 | 0 |  | 0
119 | 10-Mar-2023 | 1420.5 | 1425.5 | 5 | 1425.5 | 1436.5 | 9 | asdsd | asdsad |  | asd |  | asd | 14 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 58.33 | 2 | 0 | asdsad | 2 | sadsad
120 | 11-Mar-2023 | 1436.5 | 1436.5 | 0 | 1436.5 | 1451.5 | 15 | asd | asd |  | asd |  | asd | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 62.5 | 0 | 0 | asd | 0 | asd
121 | 12-Mar-2023 | 1451.5 | 1458.5 | 7 | 1458.5 | 1458.5 | 0 | EX 23 | asd |  | asd |  | asd | 7 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 29.17 | 0 | 0 | asd | 0 | asd
122 | 21-Mar-2023 | 1616 | 1616 | 0 | 1616 | 1616 | 0 | asdasd |  |  | asd |  | asdasd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 0 | 0 | 0 | 0 |  | 0
TOTAL |  |  |  | 347 |  |  | 351 | [6 empty] | 698 | 36 | 3 | 1 | 1495 | 1 | 21.75 | 406.5 | 12.75 | 51 | 36 | 2036 | 126.5 | 2 | 128.5 | 22 | 3 | 8 | 5 | 28.5 | 66.5 | 97.7289 | 2925 | 0 | 25.1816 | 7 | 2 |  | 5
| Prepared by, |  |  | Acknowledge by, |  |  | Checked by, |  |  | Approved by,
| Name: |  |  | Name: |  |  | Name: |  |  | Name:
| Position: |  |  | Position: |  |  | Position: |  |  | Position:
| Date: |  |  | Date: |  |  | Date: |  |  | Date: