## EX 23
Record of HM
Equipment |  |  | : | Excavator
Specification |  |  | : | KOMATSU, HB365-1
UA Asset Number |  |  | : | EXH3001T
User Number |  |  | : | EX 23
Attachment Name |  |  | : | ASD, ASDASD, ASDASDASD, ASDSAKDJL,
User |  |  | : | PT. BUMI SUKSESINDO
Location |  |  | : | BANYUWANGI
Periode |  |  | : | 26 May 2023 s/d 29 February 2024 = 280 Days
No. | Date | Hours Meter (HM) | [5 empty] | Attachment Name | Remark | Day |  | Night |  | Total HM | Delay | [9 empty] | Total Delay | IDLE |  | Total Idle | BREAKDOWN |  |  |  |  | Total Breakdown | PA(%) | Total All | Check | UA(%) | Refueling | [5 empty] | DEDUCTION | Day Shift |  | Night Shift
|  | Day Start | Day Finish | Total Shift 1 | Night Start | Night Finish | Total Shift 2 |  |  | Operator | Lokasi | Operator | Lokasi |  | Refueling | Blasting Activity | Pindah Alat | Tunggu Alat Lain | Cek Ban | Tool Box | Hujan | Prestart | Makan | Cuaca (Basah, Kabut) |  | No Job | Lain-Lain |  | Service | Progress Repair | Waiting Part | Waiting Man Power | No Operator | [5 empty] | Day Refueling | HM | Day PIC | Night Refueling | HM | Night PIC
1 | 26-May-2023 | 1710 | 1710 | 0 | 1710 | 1710 | 0 | asd |  | Aang Harianto | asd | Aang Harianto | asd | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 0 | 0 | 1,710.00 |  | 0 | 1,710.00 |  | 0 | 0 |  | 0
2 | 27-May-2023 | 1710 | 1730 | 20 | 1730 | 1734 | 4 | asdasd |  |  | dasds |  | asdsd | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 100 | 0 | 1,730.00 |  | 0 | 1,734.00 |  | 0 | 0 | asd | 0 | asd
3 | 28-May-2023 | 1734 | 1746 | 12 | 1746 | 1750 | 4 | asdasdasd |  | Abdul Azis | asdasd | Abdul Azis | asddas | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 66.67 | 500 | 1,746.00 |  | 300 | 1,750.00 |  | 0 | 0 |  | 0
4 | 29-May-2023 | 1750 | 1760 | 10 | 1760 | 1770 | 10 | asdsakdjl |  | Abdul Halim | asd | Abdul Halim | sadad | 20 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 24 | 0 | 83.33 | 200 | 1,760.00 | Abdul Azis | 300 | 1,770.00 | Akbar Anwar | 0 | 0 |  | 0
TOTAL |  |  |  | 42 |  |  | 18 | [6 empty] | 60 | 8 | 0 | 4 | 24 | 0 | 0 | 0 | 0 | 0 | 8 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 96 | 0 | 62.5 | 0 | 0 |  | 0
| Prepared by, |  |  | Acknowledge by, |  |  | Checked by, |  |  | Approved by,
| Name: |  |  | Name: |  |  | Name: |  |  | Name:
| Position: |  |  | Position: |  |  | Position: |  |  | Position:
| Date: |  |  | Date: |  |  | Date: |  |  | Date: